ADAPTIVE COMPOSITE MARKET STRESS INDEX (A-CMSI) Version 2.0 — Complete Research & Implementation Workflow Now includes: Ablation Study • Early Warning Analysis • Crisis Detection F1 • Sensitivity Analysis Ayush Anand ¦ B.Sc. Data Science & AI ¦ Christ University Delhi NCR ¦ CAI Research Team

| Assets AAPL · MSFT · SPY | Period 2015–2025 | Languages R + Python | Steps 70 Steps | Target Finance Research Letters |
| --- | --- | --- | --- | --- |

# What's New in This Version

Version 1 gave you the full modeling pipeline. Version 2 adds four critical upgrades that directly answer the reviewer question: why should anyone care about your index?

| Addition | What it proves | Where in paper |
| --- | --- | --- |
| Rigorous Weight Math | Exact derivation of w_i(t) — not a heuristic, a real algorithm | Methodology §4.5 |
| Ablation Study | Every component (GARCH, HMM, EVT) contributes — proven with numbers | Results §5.4 |
| Early Warning Analysis | A-CMSI rises X days before crash — index is actually useful | Results §5.5 |
| Crisis Detection F1 | Precision/Recall/F1 on drawdown prediction — objective performance metric | Results §5.6 |
| Sensitivity Analysis | Results hold across different entropy window sizes — methodology is robust | Results §5.7 |
| External Index Comparison | Compare vs KC-FSI and St. Louis FSI — shows unique information content | Results §5.8 |

# Master Timeline — 4 Months

| Month | Focus | Key Deliverable | Hrs/Week |
| --- | --- | --- | --- |
| Month 1 | Data pipeline, EDA, stationarity, structural breaks, cointegration | Clean dataset, ADF/KPSS table, Bai-Perron breakpoints, ECM output | 20–25 |
| Month 2 | GARCH V(t) + HMM P(t) + EVT T(t) — each validated individually | Three validated output series: V(t), P(t), T(t) | 20–25 |
| Month 3 | Adaptive weight engine + A-CMSI + ablation + early warning + validation | Full A-CMSI series, ablation table, early-warning lead times, DM test | 25–30 |
| Month 4 | Paper writing + visualizations + SSRN + journal submission | Submitted manuscript, SSRN preprint live | 20 |

| PHASE 1 Data Acquisition & Cleaning | Timeline: Month 1 · Weeks 1–2 Tools: R: quantmod, xts, zoo |
| --- | --- |

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 1 | Download Data | getSymbols() in R. Pull AAPL, MSFT, SPY adjusted close + volume. Jan 2015–Dec 2025. Save raw CSV immediately. | R |
| 2 | Date Alignment | xts::merge.xts() on common trading days. Drop non-overlapping dates. Verify 2,515 rows (10 years of trading days). | R |
| 3 | Missing Values | na.locf() forward fill. Flag any gap > 3 consecutive days in a separate log. Document in Data section of paper. | R |
| 4 | Log Returns | r_t = log(P_t / P_{t-1}) for each asset. This is your primary series for ALL downstream modeling. Never use raw prices. | R |
| 5 | Rolling Features | 21-day rolling mean, rolling variance. Rolling pairwise correlations: AAPL-MSFT, AAPL-SPY, MSFT-SPY. | R |
| 6 | Export Clean Data | Export master CSV with columns: date, aapl_ret, msft_ret, spy_ret, rolling features. Load this in Python too. | R/Python |

| PHASE 2 Exploratory Analysis | Timeline: Month 1 · Weeks 2–3 Tools: R: ggplot2, tseries, strucchange |
| --- | --- |

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 7 | Price & Return Plots | Plot adjusted close and log returns for all 3. Annotate: COVID crash Mar 2020, Fed hike Jan 2022, SVB Mar 2023, AI rally Nov 2023. | R |
| 8 | Correlation Heatmaps | Rolling 63-day pairwise correlations. Do correlations spike toward 1.0 during stress? That's your first EDA finding. | R |
| 9 | ADF Test | adf.test() on raw prices, log returns, first differences. Decision table: series × test × conclusion (I(0) or I(1)). | R |
| 10 | KPSS Test | kpss.test() as confirmation. If ADF and KPSS agree → confident stationarity decision. If they disagree → report both. | R |
| 11 | Bai-Perron Test | breakpoints() from strucchange on return series. Expect breaks near Mar 2020, Jan 2022. Document date + F-statistic. | R |
| 12 | Chow Test | sctest() to confirm Bai-Perron breaks. Report p-value. These break dates will reappear in every downstream analysis. | R |

| PHASE 3 Market Structure — Cointegration | Timeline: Month 1 · Week 4 Tools: R: urca, vars |
| --- | --- |

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 13 | Johansen Test | ca.jo() on price levels. Test all 3 pairs. Document trace statistic vs 5% critical value. State conclusion clearly. | R |
| 14 | Error Correction Model | If cointegrated: cajorls(). Extract adjustment speed alpha and equilibrium residuals. Slower alpha = weaker long-run link. | R |
| 15 | ECM Interpretation | Document: does SPY drive tech stocks? How many days to restore equilibrium after shock? This is Layer 1 of your paper's narrative. | R |

| PHASE 4 ARIMA Baseline | Timeline: Month 2 · Week 1 Tools: R: forecast |
| --- | --- |

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 16 | ACF/PACF | Plot for log returns of each asset. Identify AR(p) and MA(q) order candidates. Expect near-white-noise (EMH result). | R |
| 17 | ARIMA Fitting | auto.arima() + manual AIC/BIC grid search. Fit best model per asset. ARIMA is your mean-process and forecast baseline. | R |
| 18 | Residual Extraction | Extract innovation residuals from ARIMA. These feed directly into GARCH. Check: residuals should be uncorrelated. | R |
| 19 | Diagnostics | Ljung-Box on residuals. Jarque-Bera normality. If residuals show ARCH effects (ArchTest p < 0.05) → GARCH is justified. | R |

| PHASE 5 GARCH/EGARCH — Volatility Score V(t) | Timeline: Month 2 · Week 2 Tools: R: rugarch, FinTS |
| --- | --- |

Output of this phase V(t) = normalized conditional volatility for each asset, daily series 2015–2025. This is Component 1 of your A-CMSI.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 20 | ARCH LM Test | ArchTest() on ARIMA residuals. Must confirm ARCH effects before modeling. If p > 0.05, GARCH is not justified — report this. | R |
| 21 | GARCH(1,1) Fit | ugarchspec + ugarchfit with normal and Student-t errors. Compare AIC. Student-t usually wins for financial returns. | R |
| 22 | EGARCH(1,1) Fit | Repeat with EGARCH spec. Check gamma: if negative and significant → leverage effect confirmed. Bad news = more volatility than good news. | R |
| 23 | Model Selection | Compare GARCH vs EGARCH: AIC, BIC, Nyblom stability test, sign bias test. Select winner per asset. Likely EGARCH wins. | R |
| 24 | Extract V(t) | sigma(t) from best model. Normalize: V(t) = (sigma(t) - rolling_mean) / rolling_sd using 252-day window. Clip to [-3,3]. | R |

| PHASE 6 Hidden Markov Model — Panic Probability P(t) | Timeline: Month 2 · Week 3 Tools: Python: hmmlearn, numpy |
| --- | --- |

Output of this phase P(t) = posterior probability of Panic state at each day, daily series 2015–2025. This is Component 2 of your A-CMSI AND drives the adaptive weight engine.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 25 | Input Features | Feed HMM: log returns, V(t) from GARCH, 21-day rolling vol, rolling skewness. Standardize all features before fitting. | Python |
| 26 | Fit Gaussian HMM | GaussianHMM(n_components=3). Fit on full sample. Multiple random restarts (n_iter=200). Take best log-likelihood run. | Python |
| 27 | Label States | Rank states by mean return + variance. Lowest mean + highest var = Panic. Highest mean = Bull. Middle = Neutral. | Python |
| 28 | Regime Validation | Plot posterior probabilities over time. Panic state MUST activate during COVID Mar 2020 and inflation shock Jan 2022. If not, refit. | Python |
| 29 | Extract P(t) | P(t) = predict_proba()[:,panic_state]. Already 0-1 range. Plot against SPY drawdowns to visually confirm alignment. | Python |
| 30 | Transition Matrix | Document A matrix. Report: how persistent is each regime? Panic regime persistence is a key finding for your paper. | Python |

| PHASE 7 Extreme Value Theory — Tail Risk Score T(t) | Timeline: Month 2 · Week 4 Tools: Python: scipy, pyextremes |
| --- | --- |

Output of this phase T(t) = rolling CVaR normalized as tail-risk score, daily series 2015–2025. This is Component 3 of your A-CMSI.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 31 | Mean Excess Function | Plot MEF for each asset's loss series. Find threshold u where MEF is approximately linear. This is your GPD threshold. | Python |
| 32 | Fit GPD | genpareto.fit() on exceedances above u. Estimate shape xi (tail heaviness) and scale sigma. xi > 0 = heavy tail confirmed. | Python |
| 33 | Threshold Sensitivity | Refit at 90th, 95th, 99th percentile thresholds. If xi and sigma are stable across thresholds → robust fit. Report all three. | Python |
| 34 | VaR + CVaR | Compute 95% and 99% VaR and CVaR from fitted GPD. These are static risk metrics. Put in a clean table in your paper. | Python |
| 35 | Rolling T(t) | 252-day rolling window. Refit GPD each day. T(t) = CVaR_99(t). Normalize same as V(t). This captures time-varying tail risk. | Python |

| PHASE 8 Wavelet Analysis | Timeline: Month 3 · Week 1 Tools: Python: PyWavelets, pycwt |
| --- | --- |

Enrichment layer — not a CMSI component. Strengthens the paper's narrative about multi-scale market structure. Cut this if Month 3 runs long.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 36 | Continuous Wavelet Transform | Morlet CWT on log returns of each asset. Scalogram: x=time, y=frequency, color=power. Identify dominant cycles. | Python |
| 37 | Wavelet Coherence | Coherence between AAPL-MSFT, AAPL-SPY. Does synchronization increase during stress? This should align with P(t) spikes. | Python |
| 38 | Spectral Interpretation | Document: 20-day cycle (monthly rebalancing), 60-day (quarterly), annual. Note COVID disrupts all cycles simultaneously. | Python |

| PHASE 9 Build Adaptive CMSI — Core Contribution | Timeline: Month 3 · Weeks 1–2 Tools: Python: numpy, pandas, scipy |
| --- | --- |

★ NOVEL CONTRIBUTION: This is the novel part. Every step here is a methodological contribution. Build carefully and document every decision.

## Step 1 — Normalize All Three Components

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 39 | Z-score Normalize | For each component X_i(t): Z_i(t) = (X_i(t) - mu_252) / sigma_252 using trailing 252-day rolling stats. Clip to [-3, 3]. | Python |

## Step 2 — Compute Information Entropy Weights

Entropy Weight Formula — derive this explicitly in your paper For each component i over trailing window W (default W=63 days): 1. Normalize to probability distribution: p_i(t) = ¦Z_i(t)¦ / sum_j ¦Z_j(t)¦ 2. Shannon entropy: H_i(t) = -sum_t [ p_i(t) * log(p_i(t)) ] 3. Higher entropy = more uncertainty = signal is more active = deserves more weight 4. Base entropy weight: e_i(t) = H_i(t) / sum_j H_j(t)

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 40 | Compute Entropy | Rolling 63-day entropy for V(t), P(t), T(t) separately. Plot all three entropy series — they should diverge during stress. | Python |
| 41 | Base Entropy Weights | e_V(t), e_P(t), e_T(t) that sum to 1. These are your data-driven base weights before regime adjustment. | Python |

## Step 3 — Apply HMM Regime Multipliers

Regime Factor Table — document this as a formal design choice These multipliers encode the economic logic of your index: Regime w_V multiplier w_P multiplier w_T multiplier Bull 1.3 0.8 0.9 Neutral 1.0 1.0 1.0 Panic 0.8 1.1 1.4 Panic regime boosts T(t) because tail risk is the most relevant signal in a crash. Bull regime boosts V(t) because normal volatility dynamics dominate. Use soft multipliers: regime_factor_i(t) = sum_s [ P(state=s ¦ t) * multiplier_i_s ] This uses posterior probabilities, NOT hard state assignments. Smoother transitions.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 42 | Soft Regime Factors | For each day: regime_factor_i(t) = sum over states s of [P(s¦t) * multiplier_i_s]. Uses full posterior, not hard labels. | Python |
| 43 | Combined Raw Weights | raw_i(t) = e_i(t) * regime_factor_i(t). Combine entropy base with regime adjustment. | Python |
| 44 | Normalize Final Weights | w_i(t) = raw_i(t) / sum_j raw_j(t). Ensures weights sum to 1 every day. Enforce minimum weight of 0.05 per component. | Python |
| 45 | Plot Weight Dynamics | Plot w_V(t), w_P(t), w_T(t) over time on same chart. Should clearly see w_T spike during COVID and 2022. This is a key figure. | Python |

## Step 4 — Construct A-CMSI

Final Formula A-CMSI(t) = w_V(t) * V(t) + w_P(t) * P(t) + w_T(t) * T(t) Compute per asset: CMSI_AAPL(t), CMSI_MSFT(t), CMSI_SPY(t) Compute portfolio-level: CMSI_portfolio(t) = mean of all three This is your headline series. Every validation test runs on CMSI_portfolio(t).

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 46 | Compute A-CMSI | Apply formula daily. Output: one time series per asset + one portfolio-level series. Store all in master DataFrame. | Python |
| 47 | Crisis Event Plot | Plot CMSI_portfolio(t) 2015–2025. Annotate: COVID (Mar 2020), Inflation shock (Jan 2022), SVB (Mar 2023), AI rally (Nov 2023). | Python |

| PHASE 10 Ablation Study | Timeline: Month 3 · Week 2 Tools: Python: numpy, pandas |
| --- | --- |

★ NOVEL CONTRIBUTION: Proves each component contributes. Reviewers expect this. One extra table that significantly strengthens the paper.

Build 6 variants of CMSI. Compare all against the same validation targets. Report RMSE, MAE, directional accuracy.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 48 | Equal-Weight CMSI | w_V = w_P = w_T = 1/3 always. Simplest possible baseline. This is Baseline 1. | Python |
| 49 | PCA-Weight CMSI | PCA on [V,P,T] matrix. PC1 loadings as weights. Static over full sample. Baseline 2. | Python |
| 50 | Entropy-Only CMSI | Entropy weights but NO regime adjustment. Tests whether HMM adds value over entropy alone. Baseline 3. | Python |
| 51 | No-EVT CMSI | Full A-CMSI but T(t) = 0, redistribute weight to V and P. Tests EVT contribution. | Python |
| 52 | No-HMM CMSI | Full A-CMSI but regime factors = 1.0 always (no regime adjustment). Tests HMM contribution. | Python |
| 53 | No-GARCH CMSI | Full A-CMSI but V(t) = rolling realized vol instead of GARCH. Tests GARCH contribution. | Python |
| 54 | Full A-CMSI | Your proposed model. Should outperform all 6 above on RMSE and directional accuracy. | Python |

Expected Ablation Table (put this in Results section) Model RMSE MAE Dir. Accuracy Equal-Weight CMSI 0.95 0.71 61% PCA-Weight CMSI 0.91 0.68 63% Entropy-Only CMSI 0.88 0.65 65% No-EVT A-CMSI 0.87 0.64 66% No-HMM A-CMSI 0.89 0.66 64% No-GARCH A-CMSI 0.90 0.67 63% Full A-CMSI (Proposed) 0.82 0.61 69% Note: These are illustrative numbers. Your actual results will differ. What matters: Full A-CMSI should be best row. Each ablation should be worse.

| PHASE 11 Early Warning Analysis | Timeline: Month 3 · Week 2 Tools: Python: pandas, scipy |
| --- | --- |

★ NOVEL CONTRIBUTION: The most impactful addition. Turns your index from descriptive to predictive. This is what makes reviewers say yes.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 55 | Define Drawdown Events | A drawdown event = SPY 20-day return < -10%. Identify all such events in 2015–2025. Expect 4–6 events including COVID. | Python |
| 56 | Measure CMSI Lead Time | For each drawdown event: find the last date before the crash when CMSI crossed its 90th percentile threshold. Lead = days before crash. | Python |
| 57 | Test 5/10/20 Day Leads | For each lead window: did CMSI exceed its 90th percentile at least once in the 5/10/20 days before the crash? Record yes/no per event. | Python |
| 58 | Cross-Correlation Analysis | Compute cross-correlation between CMSI(t) and realized volatility(t+k) for k = 1 to 30 days. Peak at k=X means CMSI leads vol by X days. | Python |
| 59 | Compare Baselines | Does Equal-Weight CMSI provide the same lead time? If A-CMSI leads earlier than baselines, that's a strong result. | Python |
| 60 | Early Warning Plot | For each crisis: plot CMSI(t) and SPY drawdown on same chart. Shade the lead period. This is a key paper figure. | Python |

| PHASE 12 Crisis Detection Framework | Timeline: Month 3 · Week 3 Tools: Python: sklearn, pandas |
| --- | --- |

★ NOVEL CONTRIBUTION: Turns A-CMSI into a binary classifier for crisis detection. Objective F1 metrics give reviewers hard numbers to evaluate.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 61 | Define Crisis Labels | Crisis day = 1 if SPY daily return < -3% OR 20-day drawdown > 10%. Binary label for every day 2015–2025. | Python |
| 62 | CMSI as Classifier | Crisis prediction = 1 if CMSI_portfolio(t) > threshold. Test threshold = 75th, 90th, 95th percentile of CMSI. | Python |
| 63 | Precision/Recall/F1 | sklearn.metrics. For each threshold and each CMSI variant. Report in a clean table. F1 is your headline metric. | Python |
| 64 | ROC-AUC | Plot ROC curves for all CMSI variants. AUC gives a threshold-free comparison. A-CMSI AUC should exceed baselines. | Python |

| PHASE 13 Walk-Forward Validation + Significance Tests | Timeline: Month 3 · Week 3 Tools: Python: statsmodels, arch |
| --- | --- |

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 65 | Walk-Forward Setup | Train: expanding window starting Jan 2015. Forecast: next 30 trading days. Refit GARCH+HMM+EVT+weights each roll. Roll monthly. | Python |
| 66 | Forecast Targets | Predict: next 30-day realized volatility, binary drawdown occurrence, regime transition probability. | Python |
| 67 | Compute Metrics | RMSE, MAE, directional accuracy for each CMSI variant across all walk-forward windows. Average across all folds. | Python |
| 68 | Diebold-Mariano Test | arch.utility.dm_test(). H0: equal forecast accuracy. A-CMSI vs Equal-Weight. A-CMSI vs PCA-Weight. Report DM statistic + p-value. | Python |
| 69 | Bootstrap CIs | Bootstrap 1000 samples on RMSE improvement of A-CMSI over Equal-Weight. Report 95% CI. Shows improvement is not by chance. | Python |

| PHASE 14 Sensitivity Analysis | Timeline: Month 3 · Week 3 Tools: Python: numpy, pandas |
| --- | --- |

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 70 | Entropy Window Sensitivity | Recompute A-CMSI with W=21, W=63, W=126 day entropy windows. Compare RMSE and F1 across all three. Results should be stable. | Python |

What stable means If RMSE changes by less than 5% across window sizes → methodology is robust. Report this. If RMSE changes significantly → you need to justify your window choice or pick the best one with cross-validation.

| PHASE 15 External Index Comparison (Optional but Strong) | Timeline: Month 3 · Week 4 Tools: Python + R |
| --- | --- |

Compare A-CMSI against St. Louis Fed FSI and KC-FSI. Not to outperform them — they use more variables. Goal: show your index captures unique information they miss.

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 71 | Download External Indices | St. Louis FSI: fred.stlouisfed.org/series/STLFSI4. KC-FSI: kansascityfed.org. Both are freely available weekly series. | Python/R |
| 72 | Correlation Analysis | Compute rolling 63-day correlation between A-CMSI and each external index. High correlation = index is in the same family. | Python |
| 73 | Unique Information Test | Regress A-CMSI on FSI indices. If residuals are still predictive of volatility → A-CMSI has information beyond existing indices. | Python |

| PHASE 16 Paper Writing | Timeline: Month 4 Tools: LaTeX (Overleaf recommended) |
| --- | --- |

| # | Step | What to Do / Output | Tool |
| --- | --- | --- | --- |
| 74 | Abstract | 4 sentences only: (1) problem, (2) method, (3) key finding — early warning lead time + F1 score, (4) contribution. Write last. | Writing |
| 75 | Introduction | 3 pages. Why stress matters. What existing indices miss. Your gap. Your three-sentence contribution. Paper roadmap. | Writing |
| 76 | Literature Review | 2 pages. GARCH: Engle 1982. HMM in finance: Hassan 2005. EVT: McNeil 1999. Stress indices: Hakkio & Keeton 2009. Your gap. | Writing |
| 77 | Data Section | 1 page. Assets, period, source (Yahoo Finance via quantmod), descriptive statistics table, structural break dates. | Writing |
| 78 | Methodology | 6 pages. One subsection per layer. Include all equations. Explicitly derive the weight formula. This is your most important section. | Writing |
| 79 | Results | 6 pages. Stationarity table. GARCH output table. HMM transition matrix. EVT parameters. Ablation table. Early warning table. F1 table. | Writing |
| 80 | Discussion | 2 pages. Which regime dominates when. Does A-CMSI outperform and why. Economic interpretation of COVID vs 2022 behavior. | Writing |
| 81 | Conclusion | 1 page. Restate contribution. Limitations: 3 assets, US market only, look-ahead bias in GPD threshold. Future: add macro variables. | Writing |

# Target Paper Structure

| Section | Content | Word Count |
| --- | --- | --- |
| Abstract | Problem, method, finding, contribution | 200 |
| 1. Introduction | Motivation, gap, contribution, roadmap | 800 |
| 2. Literature Review | GARCH, HMM, EVT, stress indices, gap | 600 |
| 3. Data | Assets, period, cleaning, descriptive stats | 400 |
| 4. Methodology | All 6 layers + weight derivation + formula | 2,000 |
| 5. Results | All tables + figures from phases 10–15 | 2,000 |
| 6. Discussion | Economic interpretation, regime analysis | 600 |
| 7. Conclusion | Contribution, limitations, future work | 400 |
| References | 50+ citations | — |
| TOTAL |  | ~7,000 words |

# Final Deliverables Checklist

| Deliverable | Month | Done? |
| --- | --- | --- |
| Clean dataset CSV: AAPL, MSFT, SPY log returns 2015–2025 | 1 | ☐ |
| EDA plots + stationarity table + structural break dates | 1 | ☐ |
| Cointegration results + ECM output | 1 | ☐ |
| GARCH/EGARCH fitted models + V(t) time series | 2 | ☐ |
| HMM fitted model + regime probability plots + P(t) series | 2 | ☐ |
| EVT fitted GPD + VaR/CVaR table + T(t) rolling series | 2 | ☐ |
| Wavelet scalograms + coherence plots | 3 | ☐ |
| Adaptive weight engine code (fully documented) | 3 | ☐ |
| A-CMSI time series with annotated crisis periods | 3 | ☐ |
| Ablation study table (7 model variants) | 3 | ☐ |
| Early warning lead time table + crisis plots | 3 | ☐ |
| Crisis detection Precision/Recall/F1/AUC table | 3 | ☐ |
| Walk-forward validation metrics + Diebold-Mariano results | 3 | ☐ |
| Sensitivity analysis across entropy window sizes | 3 | ☐ |
| External index comparison (optional) | 3 | ☐ |
| Full paper manuscript 7,000+ words | 4 | ☐ |
| SSRN preprint uploaded | 4 | ☐ |
| Finance Research Letters submission | 4 | ☐ |

One rule: never move to the next phase until the current one has a clean output. Start Month 1. Validate every layer. The ablation and early warning analyses will carry the paper.

That's actually the right approach.

At this stage, don't optimize the methodology prematurely.

Your research is still in the modeling phase. First build everything, then decide what survives.

I would proceed like this:

Phase A — Build Core Components

- Johansen Cointegration ✓

- ECM ✓

- LOESS detrending

- ARIMA

- GARCH / EGARCH

- HMM

- Wavelets

- EVT

Don't worry about CMSI yet.

Phase B — Build Multiple CMSIs

After you have:

- Volatility series (V_t)

- Panic probability series (P_t)

- Tail risk series (T_t)

construct:

CMSI 1 — Equal Weight

[
CMSI^{EW}_t

\frac13(V_t+P_t+T_t)
]

CMSI 2 — PCA Weight

[
CMSI^{PCA}_t

w_1V_t+w_2P_t+w_3T_t
]

where (w_i) are PC1 loadings.

CMSI 3 — Entropy Weight

[
CMSI^{ENT}_t

w_{1,t}V_t+w_{2,t}P_t+w_{3,t}T_t
]

where weights come from entropy.

CMSI 4 — Adaptive Entropy + HMM

[
CMSI^{A}_t

\tilde w_{1,t}V_t+\tilde w_{2,t}P_t+\tilde w_{3,t}T_t
]

where

[
\tilde w_{i,t}

f(HMM_t)\times w_{i,t}
]

Phase C — Then Let the Data Decide

Compare:

| Metric | EW | PCA | ENT | A-CMSI |
| --- | --- | --- | --- | --- |
| COVID Peak |  |  |  |  |
| 2022 Rate Hikes |  |  |  |  |
| 2023 Banking Crisis |  |  |  |  |
| Forecast RMSE |  |  |  |  |
| Forecast MAE |  |  |  |  |
| Crisis Detection |  |  |  |  |

Why this is the best strategy

Right now we don't know whether:

- PCA will outperform entropy

- Entropy will outperform PCA

- Adaptive weighting will add value

- Equal weights will be nearly identical

Many papers fail because researchers decide the winner before running the experiment.

Your paper becomes much stronger if:

"Four CMSI specifications were constructed and evaluated. The adaptive entropy specification demonstrated superior crisis sensitivity and forecasting performance."

Now the conclusion comes from the evidence rather than from methodology preferences.

So for now:

Finish LOESS

↓

Finish ARIMA

↓

Finish GARCH

↓

Finish HMM

↓

Finish EVT

↓

Build 4 CMSIs

↓

Compare

↓

Choose winner

That's exactly how an experimental research paper should be developed.

C(t) component might be added :
This is a clean four-component structure. But I have one issue with C(t) specifically. Let me go through each.

V(t) — perfect, no changes

"How uncertain is the market?" is exactly right. GARCH conditional volatility measures day-to-day uncertainty. The simple meaning is accurate, intuitive, and maps cleanly to the model. Keep as is.

P(t) — perfect, no changes

"How likely are we in a panic regime?" is the clearest possible description of what an HMM posterior probability means. This is your most novel component because it's doing double duty — stress signal AND weight driver. Keep as is.

E(t) — good, minor rename suggestion

The simple meaning "how likely is an extreme crash event?" is accurate. EVT/GPD doesn't model the probability of a crash per se — it models the expected severity given you're already in the tail. So technically it's more "how bad would an extreme event be?" rather than "how likely is one?" But for a table like this the distinction is minor and the intuition is right.

One thing: you've called it E(t) in this table but T(t) everywhere else in the plan. Pick one and stick to it. I'd keep T(t) — T for tail risk — because E(t) could be confused with Expected value notation which is everywhere in probability theory.

C(t) — this is where I have a problem

"Cointegration breakdown" is not the right thing to measure here, and here's why.

Cointegration is a long-run relationship between price levels. You test it once using Johansen — it either holds or it doesn't over the sample. It's not a daily time-varying signal. You can't compute a rolling cointegration breakdown score that updates every day in a meaningful way — the test requires long windows, is statistically unreliable on short windows, and changes slowly by nature.

What you actually want C(t) to measure — and what the table's simple meaning is pointing toward — is something that moves daily and captures whether normal relationships are breaking down in real time.

The right measure for that is one of these three:

Option A — Rolling cross-asset correlation

21 or 63-day rolling average pairwise correlation between AAPL, MSFT, and SPY returns. During calm periods: moderate, around 0.5–0.7. During panic: spikes toward 1.0 as everything falls together. This is exactly "are normal market relationships breaking down?" and it updates every day.

Simple meaning becomes: "Are all assets falling together?" — which is the definition of systemic panic vs idiosyncratic stress.

Option B — Correlation dispersion

Standard deviation of pairwise correlations across a rolling window. Low dispersion = all correlations similar = systemic regime. High dispersion = correlations diverging = mixed signals.

Option C — DCC (Dynamic Conditional Correlation)

More sophisticated version of Option A. Engle's DCC-GARCH model estimates time-varying correlations with proper statistical structure. More rigorous but more complex to implement.

My recommendation is Option A. It's simple, directly computable from data you already have, economically intuitive, and connects your work to the CISS methodology which uses cross-asset correlations as its central mechanism.

The corrected table

| Component | Model | What it measures | Simple meaning |
| --- | --- | --- | --- |
| V(t) | GARCH/EGARCH | Conditional volatility | How uncertain is the market? |
| P(t) | 3-state HMM | Panic regime probability | How likely are we in a panic regime? |
| C(t) | Rolling pairwise correlation | Cross-asset contagion | Are all assets falling together? |
| T(t) | EVT / GPD | Tail risk — CVaR | How severe would an extreme event be? |

Why this four-component structure is stronger than three

The original three components V(t), P(t), T(t) each captured a different statistical dimension of stress — variance dynamics, regime identity, tail severity. But they were all essentially asset-level signals. None of them explicitly captured whether stress was spreading across assets simultaneously.

C(t) adds the systemic dimension. An index can have high V(t) from one volatile stock without being systemically stressed. But when C(t) spikes alongside V(t) and P(t), that's the signature of a genuine market-wide panic — exactly what a financial stress index should detect.

This also gives you a much cleaner economic narrative for the paper. Four components, four distinct dimensions of stress:

Uncertainty → Regime → Contagion → Tail severity

That's a complete story of how a financial crisis develops, in order.